Iteration Plan
Version 1.0

Event Management System

Release 1.0

Elaboration

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 10/9/2005 | 1.0 | Identified | Chris Armstrong |

Table of Contents

Revision History	1

Table of Contents	1

Iteration Summary	1

Requirements (Features/Use Cases/Supplemental)	2

Objectives, Risks, and Evaluation Criteria	2

Resources	3

Work Breakdown Structure	3

Comments and Questions	3

Legend	3

# Iteration Summary

| Iteration # | I1 |
| --- | --- |
| Phase | Elaboration |
| Release | 1.0 |
| Start date | 9/10/2005 |
| End date | 10/12/2005 |
| # of days | 33 (4.6 business weeks) |
| Comments |  |

# Requirements (Features/Use Cases/Supplemental)

| ID | Description |
| --- | --- |
| FEAT1 | On-line event registration |
| FEAT1.3 | Email-based confirmation |
| FEAT2 | Automate billing |
| SUC2 | Register for Event |
| SUC2.8 | Accept credit card payment |
| SUC2.9 | Credit card declined |
| SUC2.10 | Billing system unavailable |
| SUC2.11 | Email system unavailable |
| SUC2.13 | Invalid attendee information |
| SUC2.15 | Invalid email address |
| SUPP1.7 | Take online credit cards |
| SUPP1.7.1 | Visa |
| SUPP4.5 | HTML 4.0 browser |
| SUPP4.6 | Send email via SMTP |
| SUPP7.2 | Allow 50 people to register at the same time |
| SUPP7.3 | Send email confirmations within 5 minutes of completing transaction |
| SUPP8.1 | Use QuickBooks v3.1 Java/XML API |
| SUPP8.3 | Use Hibernate |

# Objectives, Risks, and Evaluation Criteria

| Objective | Risk | Evaluation Criteria | Responsible | Status |
| --- | --- | --- | --- | --- |
| Determine resources required for R1.0 | Assigned architect has limited availability after 10/1 | R1.0 resource plan [outlined] | Debbie | Completed |
| Define objectives, risks, and evaluation criteria for I1 | May not focus on appropriate elaboration activities | I1 iteration plan [detailed] | Debbie | Completed |
| Refine high-level scope of R1.0 | Scope not clear | R1.0 vision [detailed] | Janet | Not reviewed |
| Identify all likely risks | Organizational or technical issues discovered late that dramatically impact success | Risk list [outlined] | Debbie | Mostly |
| Establish development environment | Team may not have resources for managing work products; tools not ready to go | Development environment [outlined] Configuration management plan [outlined] CM repository | Jeremy | Partially |
| Identify objectives of next iteration | Uncertainty about next set of objectives for second elaboration iteration | I2 iteration plan [identified] | Debbie | Not started |
| Develop communication strategy | Lack of shared understanding by IT about PI project; no agreed upon approach to organizational communication | Communication plan [outlined] | Janet | Not reviewed |
| Assess appropriateness of release 1.0 vision, plans, and business case | Lack of stakeholder concurrence and confidence in approach and business value | I1 iteration assessment | Debbie and Janet | Not started |
| Develop SUC2: BF and AF1 | Don’t clearly understand needs of attendee users | SUC2 [detailed] Related test cases Analysis view | Tom and Ron | Mostly |
| Implement online credit card payments | Haven’t done credit cards via QuickBooks before | Payment subsystem Architecture and logical views | Steve | Mostly |
| Implement sending email via SMTP | Haven’t done SMTP email via Java Mail API before | Email subsystem Architecture and logical views | Jeremy | Completed |
| Verify performance requirements | Unable to prove system supports performance requirements | Related test cases | John | Completed |
| Implement persistence mechanism | Haven’t done persistence using Hibernate before | Persistence subsystem Architecture and logical views | Steve and Jeremy | Mostly |
| Build initial data model | May not understand core data requirements | Data model [identified] Data view | Holly | Completed |
| Establish test environment | No suitable performance testing environment | Test environment | John | Completed |

# Test Cases

| ID | Name | Type | Requirements | Status |
| --- | --- | --- | --- | --- |
| TC2.1 | New attendee successfully registers for single event using purchase order | F | SUC2, SUPP8.3, SUPP4.5 | Passed |
| TC2.3 | New attendee successfully registers for single event using Visa card | F | SUC2, SUC2.8, SUPP1.7.1 | Passed |
| TC2.6 | New attendee unsuccessfully registers for single event using Visa card | F | SUC2, SUC2.8, SUC2.9, SUPP1.7.1 | Passed |
| TC2.7 | New attendee unsuccessfully registers for single event – billing system unavailable | F | SUC2, SUC2.10, SUPP8.1 | Failed |
| TC2.8 | New attendee unsuccessfully registers for single event – email system unavailable | F | SUC2, SUC2.11, SUPP4.6 | Passed |
| TC2.12 | New attendee unsuccessfully registers for single event – invalid attendee information | F | SUC2, SUC2.13 | Passed |
| TC2.16 | New attendee successfully registers for single event – sending email fails – invalid email address | F | SUC2, SUC2.15, SUPP4.6 | Passed |
| TC2.22 | New attendee unsuccessfully registers for single event – 50 simultaneous users | P | SUC2, SUPP7.2 | Not executed |
| TC2.31 | New attendee unsuccessfully registers for single event – email sent within 5 minutes | P | SUC2, SUPP7.3 | Passed |

# Resources

| Description | Estimate | Actual | Comments |
| --- | --- | --- | --- |
| Internal resources |  |  |  |
| External resources |  |  |  |
| Software resources |  |  |  |
| Hardware resources |  |  |  |
| Other resources |  |  |  |

# Work Item List

| Objective | # | Task | Assigned To | Start Date | End Date | Effort | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 1 | Review project resource needs |  |  |  |  |  |
|  | 2 | Identify resources |  |  |  |  |  |
|  | 3 | Meet with resource managers |  |  |  |  |  |
|  | 4 | Assemble resource plan |  |  |  |  |  |
|  | 5 | Review resource pan |  |  |  |  |  |
| 9 | 1 | Detail use case SUC2 |  |  |  |  |  |
|  | 2 | Review use case SUC2 |  |  |  |  |  |
|  | 3 | Analyze use case SUC2 |  |  |  |  |  |
|  | 4 | Update architecture views |  |  |  |  |  |
|  | 5 | Design components |  |  |  |  |  |
|  | 6 | Implement components |  |  |  |  |  |
|  | 7 | Implement tests |  |  |  |  |  |
|  | 8 | Execute tests |  |  |  |  |  |

# Comments and Questions

None

# WBS Task Legend

Identified task (but not started)

In-progress task

Completed task

# Footnotes

Risks have not been consolidated in a separate risk list but do appear in the iteration plans

The IBM Rational Team Unifying Platform (RequisitePro, RUP, ClearQuest, SoDA, ProjectConsole) was successfully installed on the tool specialist’s machine; has not been deployed to any team members yet. Rational Software Architect has not been installed anywhere yet

Were unable to hold steering committee business ROI review meeting due to lack of resources and availability

Couldn’t get billing system API to work

Couldn’t get billing system API to work

Didn’t get a chance to see how stored procedures and XML data sources work with Hibernate

Functionality, Usability, Reliability, Performance, Supportability, Constraint