## Product Backlog
Version | 1,0 |  | Legend | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7
Date | 2009-09-21 |  | date | 2009-09-11 | 2009-10-16 | 2009-11-13 | 2009-12-11
#ID | add diagram, control, open diagram, delete, filter | Scope | Details | Sprint / Milestone | Priority | Workload | In charge | Traceability | Test Id | Posponed in sprint
1 | I can create sub models | Collaborative work | requires delete UML and DI dependencies from the backbone | Sprint 4 |  |  | Atos Origin | Covered requirement | Example of Test ID
2 | I can create a sequence diagram with main (common) features | Sequence | lifelines, combinedFragments, messages (partial), guard, interaction overviews | Sprint 2 |  |  | Atos Origin
3 | I can create a sequence diagram with advanced features | Sequence | part decomposition, gates… | Sprint 4 |  |  | Atos Origin
4 | I can create a composite structure diagram with main features | Composite |  | Sprint 3? |  |  | CEA
5 | I can create a state machine diagram and make the main features | State Machine |  | Sprint 3?
6 | I can create an activity diagram with main features | Activity |  | Sprint 5?
7 | I can create and edit a timing diagram | Timing diagram |  | Sprint 6
8 | I can manage (customize) model properties in a dedicated view | EEF properties | for advanced users (administrators) | Sprint 5?
9 | I can create a profile using the diagram editor | Profile |  | Sprint 4? |  |  | CEA?
10 | I can navigate in a model tree view and interact with it | Model explorer / Outline | add diagram, control, delete, filter, | Sprint 4? |  |  | Moskitt?
11 | I can create and manage SysML models | SysML | activate SysML diagrams and SysML profile | Sprint2
12 | I can create and edit properly all the features of a Class diagram | Class | fix critical or blocking bugs | Sprint 3? |  |  | CEA
13 | I can create and edit properly all the features of a Use Case diagram | Use case | fix critical or blocking bugs | Sprint 3 |  |  | Atos Origin
14 | I can manage a Papyrus model with a single resource | model + diagrams | Encapsulation of DI, notation and EMF | Sprint 4 |  |  | Atos Origin
15 | I can install Papyrus feature in an Eclipse Platform | continuous Integration | P2, update site | Sprint 2 |  |  | Atos origin/ Kenn?
16 | I can create a DSL based on papyrus backbone | backbone | advanced user : requires delete UML and DI dependencies from the backbone | Sprint 3 |  |  | Atos origin
17 | integrate documentation generation | Models | from TOPCASED | Sprint 5? |  |  | Atos origin
18 | integrate OCL editor | UML constraints | from TOPCASED | Sprint 4 |  |  | Atos origin
19 | I can create and edit Block Definition Diagram | BDD |  | Sprint 3 |  |  | Atos origin
20 | I can create and edit Internal Block Diagram | IBD |  | Sprint 4 |  |  | Atos origin
21 | I can create and edit a parametric diagram | PARA |  | Sprint 5
22 | I can create and edit a requirement diagram | REQ |  | Sprint 6

## Sprint Backlog M2
Parameter |  | TaskId | L1 | L2 | Summary | Comment | Priority | Owner | Status | Plan Est | Actual | Task Est | Rem1 | Rem2 | Rem3 | Rem4 | Rem5 | Rem6 | Rem7 | Rem8 | Rem9 | Rem10 | Rem11 | Rem12 | Rem13 | Rem14 | Rem15
Days | 15 | [10 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Dates | [12 empty] | 2009-09-14 | 2009-09-15 | 2009-09-16 | 2009-09-17 | 2009-09-18 | 2009-09-21 | 2009-09-22 | 2009-09-23 | 2009-09-24 | 2009-09-25 | 2009-09-28 | 2009-09-29 | 2009-09-30 | 2009-10-01 | 2009-10-02
Idealized | 1 | [11 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Remaining | [9 empty] | 0 | 0
Capacity | 4 | [10 empty] | 60 | 56 | 52 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0
Id03 |  | 1 | I can install Papyrus feature in an Eclipse Platform | create releng plugin to configure build | [I can install Papyrus feature in an Eclipse Platform] create releng plugin to configure build | task comment |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Id03 |  | 2 | I can install Papyrus feature in an Eclipse Platform | contact project director to set up the papyrus build for SVN | [I can install Papyrus feature in an Eclipse Platform] contact project director to set up the papyrus build for SVN | task comment |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Id03 |  | 3 | I can install Papyrus feature in an Eclipse Platform | upgrade all the features and create map file | [I can install Papyrus feature in an Eclipse Platform] upgrade all the features and create map file | task comment |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Id13 |  | 4 | I can manage a Papyrus model with a single resource |  | [I can manage a Papyrus model with a single resource] | task comment |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Id13 |  | 5 | I can manage a Papyrus model with a single resource |  | [I can manage a Papyrus model with a single resource] | task comment |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Id13 |  | 6 | I can manage a Papyrus model with a single resource |  | [I can manage a Papyrus model with a single resource] | task comment |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Id13 |  | 7 | I can manage a Papyrus model with a single resource |  | [I can manage a Papyrus model with a single resource] | task comment |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical feature1 |  | 8 | Backbone refactoring | Clean UML dependencies from the backbone | [Backbone refactoring] Clean UML dependencies from the backbone | required task for control mode |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical feature2 |  | 9 | Backbone refactoring | Refactor existing DIResourceSet to use the one from EMF | [Backbone refactoring] Refactor existing DIResourceSet to use the one from EMF |  |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical feature3 |  | 10 | Sash editor refactoring | Delete dependency on old papyrus di meta model | [Sash editor refactoring] Delete dependency on old papyrus di meta model |  |  |  | Not Started |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insert before this line,always leave one blank line above