## Sheet1
Helios Train Requirements
Category | Item | Status | Owner | Timeframe | Could be considered Exceptions? | Non-committer work | Committer work | Comments / Actions
Do the basics ... Early | Projects must have stated their intent to do so | ok
| Be in a build for the composite site aggregation by M4 | Ongoing | gep | M4 | 0 | 0 | 8 | - Needs a committer to check build files and replace eclipse version; - Needs a committer to update helios build files (Pastore has been granted access to these files, by David Williams); - Estimate considers the committers knows which files to change;
| Be in a build for the composite site aggregation by M4 | open | Daniel Pastore | M4 | 0 | 1 | 0 | - Just needs to update EPP files - Can be done just after a successful build
Planning | All projects must have their project plan in the Eclipse Foundation standard XML Format | ongoing | gep | M4 | 0 | 16 | 0 | - Update project plan from previous version
| Commitment to participating the SR1 and SR2 simultaneous maintenance releases | ok |  |  | 0 | 0 | 0 | - Just statement to participate
Communication | At least one person from each project in a Simultaneous Release must subscribe to cross-project mailing list | ok | Gorkem |  | 0 | 0 | 0 | - Needs a committer to be subscribed
| At least one person from each project must subscribe to cross-project bugzilla inbox | ok | Gorkem |  | 0 | 0 | 0 | Done
| Your representative to the Planning Council, either from PMC or Strategic Member, must attend PC meetings and represent you there | Ongoing | Gorkem |  | 0 | 0 | 0 | Gorkem to be nominated as Project Lead (at least until Helios release)
IP Documentation | Projects must have their IP Logs approved. The ones for M5 and M6 will be understood to be "drafts" but for most projects the IP Logs should be relatively complete by M7 | Ongoing | Gorkem | M5, M6, M7 | 0 | 0 | 1 | - Needs to update IPlog flags on bugs; - Decide which bugs to update (same from previous release?) - Approx. 1h to update 20 bugs
Release Review | The release review archival materials must be complete by the date specified by the EMO, which is usually staged in earlier than for a usual release. (Typically RC2.) | Ongoing | gep | RC2 | 0 | 2 | 0 | - Update from previous version
| A PMC must provide their approval in writing, in the form of a short summary of their projects that are requesting review and summary of the PMC's discussion | open
| The public review calls will be organized based on Top Level Project, and at least one PMC member should be on that call to give very brief overview of projects that are requesting the release review (not to exceed 5 minutes, at the very most) | open |  |  | 0 | 6 | 0 | - Update from previous version
| In addition to the ordinarily required Release Review Archival Materials, all Projects participating in yearly Release agree to provide a checklist-with-detail form that describes their compliance (or not) with all of the criteria items described in this document | Ongoing | gep |  | 0 | 0 | 2 | - Needs a committer to update Release Tracking in the Portal area
Play well with others ... to be in common repository | Communication: Build team members (or their designated alternates) from each project may be asked to provide direct communication channels: phone, mail, IM, IRC and at least one build team member must be "on call" during the milestone integration periods | ok | gep |  | 0 | 0 | 0 | Done
| API. Projects should leverage only published APIs of dependencies. All deviations must be documented in bugzillas. | ongoing |  |  | 0 | 8 | 0 | - Import projects locally and search for dependencies
| Message Bundles. Projects must use Eclipse message bundles unless there are technical reasons not to | open
| Version Numbering. Projects must use 4-part version numbers. | open |  |  | 0 | 0 | 0 | Done with build
| OSGi bundle format. All plug-ins (bundles) must use the true bundle form | open
| Execution Environment. All plug-ins must correctly list their Bundle Required Execution Environment (BREE) | open
| Signing. Projects must use signed plugins using the Eclipse certificate | open |  |  | 0 | 0 | 0 | Done with build
| Jarred Bundles. Projects must use jarred plug-ins (with unpack=false) unless authorized by the planning council for technical exceptions. Also, nested jars should be avoided if possible since it creates problems for projects that has dependencies to such plug-ins | open |  |  | 0 | 0 | 0 | Done with build
| Re-use and share common third party jars. Any third-party plug-ins that are common between projects must be consumed via Orbit | open
| Optimization. Projects must optimize their p2 repositories to reduce bandwidth utilization and provide a better install and update experience for users | open |  |  | 0 | 0 | 0 | Done with build
| Provide p2 repository. Projects must provide their own project p2 repository for their own project and updates. In addition, they must provide their archives and metadata in a specified format and method to allow at least parts of their repository to be aggregated and mirrored to a common repository | ok |  |  | 0 | 0 | 0 | Done with build
| Capabilities. Each project will provide basic capability/activity definitions to allow for their UI contributions to be hidden | open
| Support Translations. All strings must be externalized, and Projects must participate in Babel, meaning it is registered and available for string translation, etc. | open |  |  | 0 | 0 | 8 | - Needs to check if MTJ has externalized strings; - Needs a committer to update/create a map file and upload it to Babel site
| Excel in NL support. The Project must use ICU4J, where appropriate, to excel in NL support. (The latest ICU4J bundles will be in Orbit). | open
| Branding. Each major project (as determined by participating PMCs) must have an 'About' dialog icon with hover text that displays the provider name. Every plug-in and feature must specify a descriptive provider-name (for features), or Bundle-Vendor header (for plug-ins), as determined by the project's PMC (e.g. "Eclipse Modeling Project" rather than "Eclipse.org"). Also, Projects must contribute to the welcome page when appropriate | ok | [5 empty] | - Does MTJ have branding?
| Do No Harm. Projects must work together in any combination of any install | ok
| License text consistency. Use standard forms of license documents so it is displayed in the most usable, and concise way during install and update | open | [5 empty] | - Need to update SUA according to latest discussions.
Be a good Eclipse Citizen ... and document it | Engage Community. The Project should actively engage their community to get feedback on milestone builds, and document how they do that. One way to do this is to have a New & Noteworthy for each milestone | ongoing |  |  | 0 | 1 | 1 | - Create New & Noteworthy for the release; - Update website with new release information; - Email new release on mailing list;
| Usability. Should follow the User Interface Guidelines. The UI Checklist is a good place to start. Also, should participate in a User Interface Best Practices Working Group UI walkthrough. | ok
| Performance. Project should have measurable performance criteria that are regularly tested against. Projects should devote at least one milestone to performance and scalability improvements | open
| Test Localization. The project should use the Babel Pseudo Translation Test to verify their translatability | open |  |  | 0 | 2 | 0 | - Needs to download a PTT and test
| Enable Use with All Languages. Should design and test for enabling all languages including bidi, unicode characters, etc | open
| Builds. Projects must have a mature, stable build process: documented, scripted, repeatable, and executable by others | Ongoing | gep |  | 0 | 0 | 0 | Done with build
| Ramp Down Planned and Defined. Projects must have a written ramp down policy by M6, at the latest, and provide link. | ok | Diego | M6 | 0 | 1 | 0 | - Update from previous version
| Accessibility. Projects should design and test for accessibility compliance, following established guidelines and Eclipse fundamental techniques to achieve accessibility. | ok
| Unit Tests. Projects must have some unit tests that can verify at least basic functionality of a build or distribution. The steps to build and run the tests must be documented and executable by others | open |  |  | 16 | 0 | 0 | - Check if we can have an exception
| API Policy Defined and Documented. Typically would include how 'APIs' are distinguished from non-API and 'provisional' API, if any. It is recommended that non-API be marked with x-internal in the bundles manifest. Also, should include what the commitment is to API, how long maintained after deprecated, etc. As one example, see WTP API Policy. | open |  |  | 8 | 0 | 0 | - Needs a committer to define
| Retention Policy. Projects should define and document their retention policy. This should include both zip distributions and repositories | open |  |  | 0 | 1 | 0 | - Use same as Sequoyah
| Project Metrics. Projects should provide some summary metrics, such as number of bundles, number of committers, lines of code, number of bugs opened and fixed. This is so some statements can be made and tracked year-to-year about the size of the simultaneous release. | open
Note on C4: wgp010: This can be done, but someone needs to interact with EPP and also with teh helios team to update the new features version. I could do the job with helios build, but it would be nice if someone could work with EPP
Note on C6: wgp010: this is done... But the community can send feedbacks.
Note on C15: wgp010: I'm already updating that on the portal... But i need input in some of the fields that are open.
Note on C17: wgp010: we've done that for last year. The bugs are already opened the indicates the internal apis that are used on mtj
Note on C18: wgp010: this is done.
Note on C19: wgp010: this is done.
Note on C20: wgp010: this is done.
Note on C21: wgp010: this is done.
Note on C22: wgp010: this is done... It might have issues only if eclipse have changed the way to sign the features and plugins
Note on C23: wgp010: this is done.
Note on C24: wgp010: this is done.
Note on C27: wgp010: this is done... But we don't have na URL that describe that. As far as i remember.
Note on C28: wgp010: this is done for mtj 1.0.1. it is still necessary to add mtj 1.1.0 to babel.
Note on C30: wgp010: mtj currently uses dsdp branding
Note on C32: wgp010: i think that mtj already have the latest one... But we need to double check
Note on C33: wgp010: still need to be created.
Note on C44: wgp010: we currently only have the api tooling reports... Probably we will not have time to add more metrics.